## TERMINAL ILO
FORMATO N°17
PETROPERÚ S.A. - FICHAS DE PROYECTOS DE INVERSIÓN
CONSTRUCTION OF THE NEW ILO TERMINAL
1. Description
Located in the Ilo province, with a storage capacity of 1,053 MB and 19 unloading arms and 01 loading arm that will be carried out in 4 stages. The 1st Stage has a capacity of 296 MB, 16 unloading arms and 01 loading arm. It will also include 03 18", 14" and 10" submarine pipelines and a multi-buoy berth.
2. Components of the investment
• Civil and sanitary works. • Metalworks. • Fire fighting system. • Liquid fuel storage tanks and undersea lines. • Office furniture and equipment.
3. Funding source
PETROPERÚ S.A. own resources.
4. Physical and Financial Progress as of Q IV
Components | Financial Progress (M S/) |  |  |  | Physical Progress3 (%)
| Total Investment 1 | Cumulative execution | Budget Year 20242 | Execution Year 2024 | Scheduled as of Q I | Actual by Quarter I
Studies and Permits | 5704 | 5704 | --- | --- | - | -
Land Acquisition | 1663 | 1663 | --- | --- | - | - | inv total IP | 159376
Construction of buildings and acquisition of equipment | 153672 | 109829.9921 | 31630.3347 | 690.8585 | 28.7 | 26.4
Total | 161039 | 117196.9921 | 31630.3347 | 690.8585 | 28.7 | 26.4
1 Re-evaluation of the project approved with Board Agreement A/D No.062-2015-PP (includes the acquisition of land). Currently being updated. | [6 empty] | ACUM A DIC 2023 | 114843.1336 | 109829.9921 | Los estudios forman parte del acum
2 Approved with A/D No. 0166-2023-PP on 14.12.2023. | [6 empty] | EJEC A MAR 2024 | 690.8585
3 According to the baseline review of the project carried out in September 2023. | [7 empty] | 115533.9921
5. Main activities carried out and current situation
- In 2023, the procurement of equipment and materials was completed within the framework of the termination of the contract with Felguera I.H.I. S.A., due to which the service is executed for its preservation. - The process of reviewing the scope of the project was completed, identifying new requirements, as well as pending permitting, so it was necessary to update the detailed engineering, which is executed by AYESA Co, in order to obtain the updated investment amount. The study is expected to be completed in August of this year.