## PLANTA NINACACA
FORMATO N°17
PETROPERÚ S.A. - FICHAS DE PROYECTOS DE INVERSIÓN
CONSTRUCTION OF THE NINACACA SUPPLY PLANT
1. Description
Consists of the construction of a Supply Plant in the Department of Pasco, with a storage capacity of 7.5 MB of fuels (Phase 1), for the dispatch of Diesel B5 and Gasolines.
2. Components of the investment
• Land. • Buildings. • Liquid fuel storage tanks. • Reception and dispatch system. • Pipeline network with product pumping system. • Fire-fighting system including a pump house. • Electrical installations and other facilities.
3. Funding source
PETROPERU S.A. own resources.
4. Physical and financial progress to Q I
Components | Financial Progress (M S/) |  |  |  | Physical Progress3 (%)
| Total Investment 1 | Cumulative execution | Budget Year 20242 | Execution Year 2024 | Scheduled for Quarter I | Actual by Quarter I
Engineering and previous procedures | 1840 | 1606 | --- | --- | - | -
Land | 815 | 815 | --- | --- | - | - | inv total IP | 25138
Materials, equipment and works | 22483 | 18833.343 | 2303.8588 | 0 | 51.6 | 47.6
Total | 25138 | 21254.343 | 2303.8588 | 0 | 51.6 | 47.6
1 Investment amount approved with A/D No.066-2017-PP of 26.06.2017. Currently under review | [6 empty] | ACUM AL 2023 | 21254.343 | 18833.343
2 Approved with A/D No. 0166-2023-PP on 14.12.2023. | [6 empty] | EJEC A MAR 2024 | 0
3 According to the baseline review of the project carried out in September 2023. | [7 empty] | 21254.343
5. Main activities carried out and current situation
- The project has been halted since April 2020, initially due to the dispute resolution process with the contractor Consorcio OBS – IMECON S.A., then by contractual resolution in March 2022 and finally, because it is in the process of re-evaluation, which is estimated to conclude in July 2024. Currently, the actions strictly necessary for the preservation and conservation of the equipment and materials that are in the construction area of the project are carried out.