## TERMINAL ILO
FORMATO N°17
PETROPERÚ S.A. - INVESTMENT PROJECT SHEETS
CONSTRUCTION OF THE NEW ILO TERMINAL
1. Description
Located in the Ilo province, with a storage capacity of 1,053 MB and 19 unloading arms and 01 loading arm, it will be developed in 4 stages. The 1st Stage has a capacity of 296 MB, 16 unloading arms and 01 loading arm. It will also include 03 18", 14" and 10" submarine pipelines and a multi-buoy berth.
2. Components of the investment
• Civil and sanitary works. • Metalworks. • Fire-fighting system. • Liquid fuel storage tanks and undersea lines. • Office furniture and equipment.
3. Source of funding
PETROPERÚ S.A. own resources.
4. Physical and Financial progress to Q III
Components | Financial Progress (M S/) |  |  |  | Physical Progress3 (%)
| Total Investment 1 | Cumulative execution | Budget Year 20232 | Execution Year 2023 | Scheduled to Q III | Real to Q III
Studies and Permits | 5704 | 5704 | --- | --- | - | -
Land Acquisition | 1663 | 1663 | --- | --- | - | -
Construction of buildings and acquisition of equipment | 153672 | 107651.3434 | 16958.05 | 3505.205 | 25.8 | 25.8
Total | 161039 | 115018.3434 | 16958.05 | 3505.205 | 25.8 | 25.8
1 Re-evaluation of the project approved by Board of Directors Agreement B.A. No. 062-2015-PP (includes the acquisition of land). Currently being updated.
2 2023 Annual Budget, approved by Board Agreement No. 119-2022-PP of 12.07.2022
3 According to the baseline review of the project carried out in September 2023.
5. Main activities carried out and current situation
- Global physical progress is 25.8% vs. 25.8% scheduled. - The procurement of equipment and materials was completed within the framework of the termination of the contract with Felguera I.H.I. S.A. Because of this, preservation works are being carried out. - In September, the project scope review process concluded, so a new engineering study will be developed in order to determine the updated investment amount. - Finally, considering the re-evaluation data of the project, the technical documentation is being worked on to request from the Provincial Municipality of Ilo a new extension of the deadline for the continuation of the construction activities in the land of the terminal, as its current deadline expires on 12.31.2023.