## PLANTA PUERTO MALDONADO
FORMATO N°17
PETROPERÚ S.A. - INVESTMENT PROJECT SHEETS
CONSTRUCTION OF SALES PLANT IN PUERTO MALDONADO
1. Description
Consists of the construction of a Sales Plant in the department of Madre de Dios, with a storage capacity of 50 MB, for the dispatch of Diesel B5 and gasoline.
2. Components of the investment
• Civil and sanitary works. • Metalworks. • Fire-fighting system. • Equipment for dispatch isles. • Office furniture and equipment.
3. Source of funding
PETROPERÚ S.A. own resources.
4. Physical and Financial progress to Q III
Components | Financial Progress (M S/) |  |  |  | Physical Progress3 (%)
| Total Investment 1 | Cumulative execution | Budget Year 20232 | Execution Year 2023 | Scheduled for Q III | Real to Q III
Engineering and previous procedures | 1300 | 1699 | - | - | - | -
Land | 733 | 733 | - | - | - | -
Materials, equipment and works | 63164 | 62732.5558 | 457.0431 | 106.2164 | 59.7 | 59.7
Total | 65197 | 65164.5558 | 457.0431 | 106.2164 | 59.7 | 59.7
1 Investment amount approved with B.A. No. 120-2018-PP of 12.20.2018. It is currently being updated.
2 2023 Annual Budget, approved by Board Agreement No. 119-2022-PP of 12.07.2022
3 According to the baseline review of the project carried out in September 2023.
5. Main activities carried out and current situation
- Overall physical progress was 59.7% vs. 59.7% scheduled. - Coordination has been initiated with the contractor TECNITANQUES Ingenieros S.A.S., in order to resolve by mutual agreement Contract No. 4100008911 "Procurement and Construction Service of the New Puerto Maldonado Supply Plant" suspended since 01.01.2022, considering that to date the project is undergoing a comprehensive evaluation of its scope and investment amount. - On the other hand, the National Superintendence of State Property (SBN) is being managed to obtain the right-of-use of the area where the exterior storm drainage of the plant will be built and operated.