## PLANTA NINACACA
FORMATO N°17
PETROPERÚ S.A. - INVESTMENT PROJECT SHEETS
CONSTRUCTION OF THE NINACACA SUPPLY PLANT
1. Description
Consists of the construction of a Supply Plant in the Department of Pasco, with a storage capacity of 7.5 MB of fuels (Phase 1), for the dispatch of Diesel B5 and Gasolines.
2. Components of the investment
• Land. • Buildings. • Liquid fuel storage tanks. • Reception and dispatch system. • Piping network with product pumping system. • Fire-fighting system including a pump house. • Electrical installations and other facilities.
3. Source of funding
PETROPERÚ S.A. own resources.
4. Physical and financial progress to Q III
Components | Financial Progress (M S/) |  |  |  | Physical Progress3 (%)
| Total Investment 1 | Cumulative execution | Budget Year 20232 | Execution Year 2023 | Scheduled for Q III | Real to Q III
Engineering and previous procedures | 1840 | 1606 | --- | --- | - | -
Land | 815 | 815 | --- | --- | - | -
Materials, equipment and works | 22483 | 18660.0078 | 3337.7175 | 170.1188 | 47.5 | 47.5
Total | 25138 | 21081.0078 | 3337.7175 | 170.1188 | 47.5 | 47.5
1 Investment amount approved with Board of Directors Agreement No. 066-2017-PP of 06.26.2017. Currently being updated.
2 2023 Annual Budget, approved by Board Agreement No. 119-2022-PP of 12.07.2022
3 According to the baseline review of the project carried out in September 2023.
5. Main activities carried out and current situation
- Overall physical advancement was 47.5% vs. 47.5% scheduled. - The project has been halted since April 2020, initially due to the dispute resolution process with the contractor Consorcio OBS – IMECON S.A., then by the contract resolution in March 2022 and finally, by the comprehensive review of the project, which is estimated to conclude in October 2023. Currently, the actions strictly necessary for the preservation and conservation of the equipment and materials that are in the construction area of the project are carried out.